## Gantt Chart
Gantt Chart
| T1 Week8 | T1 Week9 | T1 Week10 | T2 Week1 | T2 Week2 | T2 Week3 | T2 Week4 | T2 Week5 | T2 Week6 | T2 Week7 | T2 Week8 | T2 Week9 | T2 Week10 | T2 Week11 | T3 Week1 | T3 Week2 | T3 Week3 | T3 Week4
General Planning for the Project
Client Meeting 20% ED&P
Group Meeting to specify member's part
Individual research stage | bar: T2 Week1
Aesthetic design planning | bar: T2 Week1 to T2 Week2
Aquiring specific parts | bar: T2 Week1 to T2 Week3
indivudual sensor circuits design | bar: T2 Week1 to T2 Week4
Motor design | bar: T2 Week1 to T2 Week4
Arduino C programming | bar: T2 Week1 to T2 Week4
Arduino hardware instalation | bar: T2 Week1 to T2 Week4
Trial with individual parts | bar: T2 Week3 to T2 Week4
Assembling the Rover | bar: T2 Week5 to T2 Week6
Presentation(Marked) 30%ED&P | bar: T2 Week7
Prototyping | bar: T2 Week8 to T2 Week9
Testing the prototype | bar: T2 Week9
Testing the whole system 1.0 | bar: T2 Week9
Report 30% EP, 45% ED&P
Improvement
Testing the whole system 2.0
Don't break it
Demo&Oral Presentation 30% EP
Finished

## meeting schedule
Week | Meeting Date | Time | Goals | To-Do s before next meeting | Comment
T1 Week8 | Wednesday | 2-4pm | 1.Assign roles 2.10 most important PDS, detailed descriptions 3. overall project structure and allocate responsibilities | 1.individual study/research on their assinged project part 2.Upload documentation on dropbox 4. Gantt Chart by Sheng and upload to dropbox and modify by the rest of the group memebers
T1 Week9 | Wednesday | 2-4pm | 1.rearrange and sucture our online dropbox ( add research, programes, sensors, mechanics , pictures etc… folders) 2. go through "client meeting" marking scheme, tick each box. 3. Discussion for details of the design of the rover
T1 Week10
T1 Week11
T1 Week12
T1 Week13
T1 Week14
T1 Week15
T1 Week16
T1 Week17
T1 Week18
T1 Week19
T1 Week20
T1 Week21
T1 Week22
T1 Week23
T1 Week24
T1 Week25
T1 Week26
T1 Week27